## Sprint 1
Sprint 1 Retrospective
The Good | Continue Doing
Early and efficient distribution of tasks among members
Dedication of every team member towards completing the tasks assigned to them at the earliest
The Bad | Start Doing - Improvement items/ Agreements on new way of working
Need to improve our foundations on Git and jira
Collision of certain tasks and slight ignorance of git features caused certain merge conflicts, that took some time off the sprint
The Ugly | Stop Doing
Difference in opinion over some elements in the srs lead to tensions within the team.Need to improve the understandability and the ability to resolve ambiguity in software requirements.
2 people sometimes unknowingly worked on the same task that led to unnecessary time wastage.