## Sprint 1 Backlog
Story # | Sprint Backlog Item | Task # | Volunteer |  | Initial Effort Estimate (hrs) | New Estimates of Effort remaining at end of | [5 empty] | Status
[6 empty] | Day1 | Day2 | Day3 | Day4 | Day5 | Day6
US001 | As a admission desk executive /pharmacist/ diagnostic center executive I want to be able to log in the hospital website with my user ID and password So that I carry out my transactions | Task 1 | Chittaranjan Sahu | Creating Blueprint of the login page( items/functionality/purpose) | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 0 | CLOSED
|  | Task 2 | RamVignesh B | Creating common template for header and footer | 5 | New Estimates of Effort remaining at end of Day1: 3; New Estimates of Effort remaining at end of Day2: 2 | CLOSED
|  | Task 3 | Ayush Saini | Create wtf form for login page | 3 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 1 | CLOSED
|  | Task 4 | Vibhor Aggarwal | Managing Sessions | 2 | [6 empty] | CLOSED | bar: New Estimates of Effort remaining at end of Day1 to New Estimates of Effort remaining at end of Day2
|  | Task 5 | MohammedAquid Mushrif | Database model creation for login page | 4 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 2 | CLOSED
|  | Task 6 | Vibhor Aggarwal | Providing access of specific functionality to specific stakeholders | 2 | 0 | 0 | 1 | 1 |  |  | CLOSED
|  | Task 7 | RamVignesh B | Creating UI for login page | 3 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 1 | CLOSED
|  | Task 8 | Vibhor Aggarwal | Testing the login page | 3 | 0 | 0 | 0 | 3 |  |  | CLOSED
|  | Task 9 | Ayush Saini | Managing Form validations | 4 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 2 | CLOSED
|  | Task 10 | RamVignesh B | Creating routes for login page | 2 | New Estimates of Effort remaining at end of Day1: 2 | CLOSED
|  | Task 11 | Ayush Saini | Integrating database in forms | 4 | New Estimates of Effort remaining at end of Day1: 1; New Estimates of Effort remaining at end of Day2: 2; New Estimates of Effort remaining at end of Day3: 1 | CLOSED
|  | Task 12 | Chittaranjan Sahu | Creating user_store table and adding data to user table | 2 | New Estimates of Effort remaining at end of Day1: 0; New Estimates of Effort remaining at end of Day2: 0; New Estimates of Effort remaining at end of Day3: 2 | CLOSED
US002 | As a admission desk executive I want to be able to capture new patient information So that I can create a new patient in the system | Task 1 | Chittaranjan Sahu | Creating Blueprint of the create patient page( items/functionality/purpose) | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 0 | CLOSED
|  | Task 2 | RamVignesh B | Importing databases for real time display of states and their corresponding cities | 5 | New Estimates of Effort remaining at end of Day1: 1; New Estimates of Effort remaining at end of Day2: 4 | CLOSED
|  | Task 3 | Ayush Saini | Create wtf form for create patient page | 3 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 1 | CLOSED
|  | Task 4 | Vibhor Aggarwal | Managing Sessions | 2 | [6 empty] | CLOSED | bar: New Estimates of Effort remaining at end of Day1 to New Estimates of Effort remaining at end of Day2
|  | Task 5 | MohammedAquid Mushrif | Database model creation for create patient page | 4 | New Estimates of Effort remaining at end of Day1: 3; New Estimates of Effort remaining at end of Day2: 1 | CLOSED
|  | Task 6 | Ayush Saini | Adding created data to database | 4 | New Estimates of Effort remaining at end of Day1: 0; New Estimates of Effort remaining at end of Day2: 3; New Estimates of Effort remaining at end of Day3: 1 | CLOSED
|  | Task 7 | RamVignesh B | Creating UI for create patient page | 4 | New Estimates of Effort remaining at end of Day1: 1; New Estimates of Effort remaining at end of Day2: 3 | CLOSED
|  | Task 8 | Vibhor Aggarwal | Testing the create patient page | 3 | New Estimates of Effort remaining at end of Day1: 0; New Estimates of Effort remaining at end of Day2: 0; New Estimates of Effort remaining at end of Day3: 1 | CLOSED
|  | Task 9 | Ayush Saini | Managing Form validations | 4 | New Estimates of Effort remaining at end of Day1: 0; New Estimates of Effort remaining at end of Day2: 3; New Estimates of Effort remaining at end of Day3: 1 | CLOSED
|  | Task 10 | RamVignesh B | Creating routes for create patient page | 2 | New Estimates of Effort remaining at end of Day1: 2 | CLOSED
US003 | As a admission desk executive I want to be able to edit existing patient information So that I can store the updated patient information in the system | Task 1 | Chittaranjan Sahu | Creating Blueprint of the update patient page( items/functionality/purpose) | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 0 | CLOSED
|  | Task 2 | Ayush Saini | Create wtf form for update patient page | 3 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 1 | CLOSED
|  | Task 3 | Vibhor Aggarwal | Managing Sessions | 2 | [6 empty] | CLOSED | bar: New Estimates of Effort remaining at end of Day1 to New Estimates of Effort remaining at end of Day2
|  | Task 4 | MohammedAquid Mushrif | Database model creation for update patient page | 4 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 2 | CLOSED
|  | Task 5 | Ayush Saini | Integrating database in forms | 4 | 0 | 0 | 1 | 3 |  |  | CLOSED
|  | Task 6 | RamVignesh B | Creating UI for update patient page | 4 | New Estimates of Effort remaining at end of Day1: 1; New Estimates of Effort remaining at end of Day2: 3 | CLOSED
|  | Task 7 | Vibhor Aggarwal | Testing the update patient page | 3 | New Estimates of Effort remaining at end of Day1: 0; New Estimates of Effort remaining at end of Day2: 0 | CLOSED
|  | Task 8 | Ayush Saini | Managing Form validations | 4 | 0 | 0 | 2 | 2 |  |  | CLOSED
|  | Task 9 | RamVignesh B | Creating routes for update patient page | 2 | New Estimates of Effort remaining at end of Day1: 0; New Estimates of Effort remaining at end of Day2: 2 | CLOSED
|  | Task 10 | Ayush Saini | Implementing actual changes in database | 4 | 0 | 0 | 2 | 2 |  |  | CLOSED
US004 | As a admission desk executive I want to be able to delete existing patient from system | Task 1 | Chittaranjan Sahu | Creating Blueprint of the delete patient page( items/functionality/purpose) | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 0 | CLOSED
|  | Task 2 | Ayush Saini | Retrieving data based on SSN ID and displaying it in respective fields | 4 | New Estimates of Effort remaining at end of Day1: 0; New Estimates of Effort remaining at end of Day2: 1; New Estimates of Effort remaining at end of Day3: 3 | CLOSED
|  | Task 3 | Ayush Saini | Integrating database in forms | 4 | New Estimates of Effort remaining at end of Day1: 1; New Estimates of Effort remaining at end of Day2: 1; New Estimates of Effort remaining at end of Day3: 2 | CLOSED
|  | Task 4 | RamVignesh B | Creating UI for delete page | 3 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 1 | CLOSED
|  | Task 5 | RamVignesh B | Creating routes for delete patient page | 2 | New Estimates of Effort remaining at end of Day1: 2 | CLOSED
|  | Task 6 | Ayush Saini | Create wtf form for delete patient page | 3 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 1 | CLOSED
|  | Task 7 | Vibhor Aggarwal | Managing Sessions | 2 | [6 empty] | CLOSED | bar: New Estimates of Effort remaining at end of Day1 to New Estimates of Effort remaining at end of Day2
|  | Task 8 | MohammedAquid Mushrif | Database model creation for delete patient page | 4 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 2 | CLOSED
|  | Task 9 | Ayush Saini | Managing Form validations | 4 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 2 | CLOSED
|  | Task 10 | Vibhor Aggarwal | Testing the delete patient page | 3 | 0 | 0 | 2 | 1 |  |  | CLOSED
|  | Task 11 | RamVignesh B | Adding Delete functionality | 3 | New Estimates of Effort remaining at end of Day1: 0; New Estimates of Effort remaining at end of Day2: 1; New Estimates of Effort remaining at end of Day3: 2 | CLOSED
US005 | As a admission desk executive I want to be able to view all the active patients currently admitted in the hospital | Task 1 | Chittaranjan Sahu | Creating Blueprint of the active patients page( items/functionality/purpose) | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 0 | CLOSED
|  | Task 2 | Vibhor Aggarwal | Managing Sessions | 2 | New Estimates of Effort remaining at end of Day1: 0; New Estimates of Effort remaining at end of Day2: 1; New Estimates of Effort remaining at end of Day3: 1 | CLOSED
|  | Task 3 | MohammedAquid Mushrif | Database model creation for active patients page | 4 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 2 | CLOSED
|  | Task 4 | Ayush Saini | Integrating database | 4 | New Estimates of Effort remaining at end of Day1: 0; New Estimates of Effort remaining at end of Day2: 1; New Estimates of Effort remaining at end of Day3: 3 | CLOSED
|  | Task 5 | RamVignesh B | Creating UI for active patients page | 3 | New Estimates of Effort remaining at end of Day1: 0; New Estimates of Effort remaining at end of Day2: 1; New Estimates of Effort remaining at end of Day3: 2 | CLOSED
|  | Task 6 | Vibhor Aggarwal | Testing the active patients page | 3 | 0 | 0 | 1 | 2 |  |  | CLOSED
|  | Task 7 | RamVignesh B | Creating routes for active patients page | 2 | New Estimates of Effort remaining at end of Day1: 0; New Estimates of Effort remaining at end of Day2: 1; New Estimates of Effort remaining at end of Day3: 1 | CLOSED
|  | Task 8 | RamVignesh B | Additional functionality: Adding Filter option to view patient with their ID or any other specific details | 3 | New Estimates of Effort remaining at end of Day1: 0; New Estimates of Effort remaining at end of Day2: 0; New Estimates of Effort remaining at end of Day3: 3 | CLOSED
US006 | As a admission desk executive I want to be able to search for a patient So that I am able to view the details | Task 1 | Chittaranjan Sahu | Creating Blueprint of the search patient page( items/functionality/purpose) | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 0 | CLOSED
|  | Task 2 | Ayush Saini | Database linking for search patient page | 4 | 0 | 0 | 3 | 1 |  |  | CLOSED
|  | Task 3 | Vibhor Aggarwal | Testing the search patient page | 3 | 0 | 0 | 1 | 2 |  |  | CLOSED
|  | Task 4 | RamVignesh B | Creating UI for search patient page | 3 | New Estimates of Effort remaining at end of Day1: 0; New Estimates of Effort remaining at end of Day2: 0; New Estimates of Effort remaining at end of Day3: 3 | CLOSED
|  | Task 5 | RamVignesh B | Creating routes for search patient page | 2 | New Estimates of Effort remaining at end of Day1: 0; New Estimates of Effort remaining at end of Day2: 0; New Estimates of Effort remaining at end of Day3: 2 | CLOSED
|  | Task 6 | Ayush Saini | Create wtf form for search patient page | 3 | 0 | 1 | 1 | 1 |  |  | CLOSED
|  | Task 7 | Vibhor Aggarwal | Managing Sessions | 2 | New Estimates of Effort remaining at end of Day1: 0; New Estimates of Effort remaining at end of Day2: 1; New Estimates of Effort remaining at end of Day3: 1 | CLOSED
|  | Task 8 | RamVignesh B | Adding proper search functionality | 3 | 0 | 1 | 1 | 1 |  |  | CLOSED
US007 | As a pharmacist I want to be able to capture the medicines issued to a patient So that I can issue new medicines for an existing patient | Task 1 | Chittaranjan Sahu | Creating Blueprint of the medicines page( items/functionality/purpose) | 2 | 0 | 0 | 0 | 2 |  |  | CLOSED
|  | Task 2 | RamVignesh B | Creating routes for medicines page | 2 | 0 | 0 | 0 | 1 | 1 |  | CLOSED
|  | Task 3 | Ayush Saini | Create wtf form for medicines page | 3 | 0 | 0 | 0 | 0 | 3 |  | CLOSED
|  | Task 4 | Vibhor Aggarwal | Managing Sessions | 2 | 0 | 0 | 0 | 0 | 2 |  | CLOSED
|  | Task 5 | MohammedAquid Mushrif | Database model creation for medicines page | 4 | 0 | 0 | 0 | 1 | 3 |  | CLOSED
|  | Task 6 | Ayush Saini | Integrating database | 4 | 0 | 0 | 0 | 1 | 3 |  | CLOSED
|  | Task 7 | RamVignesh B | Creating UI for medicines page | 3 | 0 | 0 | 0 | 2 | 1 |  | CLOSED
|  | Task 8 | Vibhor Aggarwal | Testing the medicines page | 3 | 0 | 0 | 0 | 0 | 0 | 3 | CLOSED
|  | Task 9 | Ayush Saini | Managing Form validations | 2 | 0 | 0 | 0 | 1 | 1 |  | CLOSED
|  | Task 10 | Chittaranjan Sahu | Creating medicines table and update data with medicine table | 4 | 0 | 0 | 1 | 1 | 2 |  | CLOSED
|  | Task 11 | Ayush Saini | Looking after dynamic update on availability of medicines after selection | 3 | 0 | 0 | 0 | 1 | 2 |  | CLOSED
US008 | As a diagnostics executive I want to be able to capture the diagnostocs conducted to a patient So that I can add new tests for an existing patient | Task 1 | Chittaranjan Sahu | Creating Blueprint of the diagnostics page( items/functionality/purpose) | 2 | 0 | 0 | 0 | 1 | 1 |  | CLOSED
|  | Task 2 | RamVignesh B | Creating routes for diagnostics page | 2 | 0 | 0 | 0 | 1 | 1 |  | CLOSED
|  | Task 3 | Ayush Saini | Integrating database | 4 | 0 | 0 | 0 | 0 | 2 | 2 | CLOSED
|  | Task 4 | RamVignesh B | Creating UI for diagnostics page | 3 | 0 | 0 | 0 | 2 | 1 |  | CLOSED
|  | Task 5 | Vibhor Aggarwal | Testing the diagnostics page | 3 | 0 | 0 | 0 | 0 | 0 | 3 | CLOSED
|  | Task 6 | Ayush Saini | Create wtf form for diagnostics page | 3 | 0 | 0 | 0 | 0 | 2 | 1 | CLOSED
|  | Task 7 | Vibhor Aggarwal | Managing Sessions | 2 | 0 | 0 | 0 | 0 | 2 |  | CLOSED
|  | Task 8 | MohammedAquid Mushrif | Database model creation for diagnostics page | 4 | 0 | 0 | 1 | 2 | 1 |  | CLOSED
|  | Task 9 | Ayush Saini | Managing field validations | 2 | 0 | 0 | 0 | 1 | 1 |  | CLOSED
|  | Task 10 | Chittaranjan Sahu | Creating Diagnostics table and entering data into it | 3 | 0 | 0 | 0 | 1 | 2 |  | CLOSED
US009 | As a admission desk executive I want to be able to get existing patient information So that I can raise the bill for the patient | Task 1 | Chittaranjan Sahu | Creating Blueprint of the patient billing page( items/functionality/purpose) | 2 | 0 | 0 | 0 | 0 | 0 | 2 | CLOSED
|  | Task 2 | RamVignesh B | Creating routes for billing page | 2 | 0 | 0 | 0 | 0 | 0 | 2 | CLOSED
|  | Task 3 | Ayush Saini | Create fields for patient billing page | 3 | 0 | 0 | 0 | 0 | 1 | 2 | CLOSED
|  | Task 4 | Vibhor Aggarwal | Managing Sessions | 2 | 0 | 0 | 0 | 0 | 0 | 2 | CLOSED
|  | Task 5 | MohammedAquid Mushrif | Database model creation for patient billing page | 4 | 0 | 0 | 0 | 0 | 2 | 2 | CLOSED
|  | Task 6 | Ayush Saini | Integrating database | 4 | 0 | 0 | 0 | 0 | 1 | 3 | CLOSED
|  | Task 7 | RamVignesh B | Creating UI for patient billing page | 3 | 0 | 0 | 0 | 0 | 1 | 2 | CLOSED
|  | Task 8 | Vibhor Aggarwal | Testing the patient billing page | 3 | 0 | 0 | 0 | 0 | 0 | 3 | CLOSED
|  | Task 9 | Ayush Saini | Managing PatientID validations | 2 | 0 | 0 | 0 | 0 | 1 | 1 | CLOSED
|  | Task 10 | RamVignesh B | Handling Billing Queries | 4 | 0 | 0 | 0 | 0 | 2 | 2 | CLOSED
|  | Task 11 | Ayush Saini | See that status necessarily becomes discharged and patient does not appear in view patients | 1 | 0 | 0 | 0 | 0 | 0 | 1 | CLOSED
|  |  |  | Total | 270 | 57 | 55 | 46 | 37 | 39 | 31

## Sprint 1 Burndown Chart
Day0 | Day1 | Day2 | Day3 | Day4 | Day5 | Day6
270 | 213 | 158 | 112 | 75 | 36 | 0
270 | 225 | 180 | 135 | 90 | 45 | 0